## Bill (hidden)
contract Name
BILL OF QUANTITIES NO. |  | Bill No. |  | Region |  |  | Fin. Year
Activity Group Title | [6 empty] | Month
|  | UNIT | QUANTITIES |  |  |  |  | AMOUNT
ITEM | DESCRIPTION |  | BOQ | PREVIOUS | THIS | TO-DATE | RATE | KSHS
KSHS

## Statement
COUNTY GOVERNMENT OF KERICHO
DEPARTMENT OF PUBLIC WORKS, ROADS AND TRANSPORT
FINAL PAYMENT CERTIFICATE FOR MAINTENANCE ROAD WORKS
e3 |  |  |  |  | Contractor: Kossi And Siju Ltd
Contract No. CGK/RD/MT/2015/16- 16 |  |  |  |  | IPC NO.: Final
Contract Sum: 599,225.70 |  |  |  |  | DATE: 19/03/2018
|  |  |  | Previous Certificate (Kshs) |  | This Certificate (Kshs) |  | Total (Kshs)
A. TOTAL WORK DONE |  |  |  | 0 |  | 516573.88 |  | 516573.88
B. MATERIAL ON SITE | [5 empty] | 0 |  | 0
C. VARIATION OF PRICE |  |  |  | 0 |  |  |  | 0
D. SUB-TOTAL (A+B+C) |  |  |  | 0 |  | 516573.88 |  | 516573.88
| TOTAL VALUE OF WORK |  |  | 0 |  | 516573.88 |  | 516573.88
| ADD 16% V.A.T |  |  | 0 |  | 82651.8208 |  | 82651.8208
|  | E. TOTAL PAYMENT |  | 0 |  | 599225.7008 |  | 599225.7008
|  | F ADVANCE Payment |  | 0 |  |  |  | 0
|  | G. Recovery OF ADVANCE |  | 0 |  |  |  | 0
|  | H. LESS 10% RETENTION |  |  |  | 0 |  | 0
|  | H. NET PAYMENT |  | 0 |  | 599225.7008 |  | 599225.7008
|  | I. LESS THE PREVIOUS CERTIFICATE | [5 empty] | 0
|  | NOW DUE TO CONTRACTOR |  |  |  | 599225.7008 |  | 599225.7008
Checked and
Submitted by……………………………………. Date………………. |  |  |  |  | Recommended for payment by……………………………….Date……………
| Contractors Representative | [5 empty] | County Roads Engineer
Confirmed by…………………..……………………….. |  |  | ……..Date……………………….. |  | Certified by:…………………......................………………….Date…………
| Road Inspector | [5 empty] | Chief Officer

## Summary of BQ
Contract Name: Borborwet Banda- Mereonik Road |  | Contractor : Kossi And Siju Ltd
Contract No. CGK/RD/MT/2016/17- 16 |  | IPC NO.: Final
SUMMARY OF BILL OF ITEMS |  | DATE: 19/03/2018
BILL NO. |  | TENDER | CERTIFICATE |  | AMOUNT
| DESCRIPTION | AMOUNT | PREVIOUS | THIS | KSHS
1 | PRELIMINARY AND GENERAL GENERAL ITEMS | 10000 | 0 | 10000 | 10000
4 | SITE CLEARANCE&TOP SOIL STRIPPING | 37200 | 0 | 37200 | 37200
5 | EARTHWORKS | 0 | 0 | 0 | 0
8 | CULVERT AND DRAINAGE WORKS | 26400 | 0 | 26400
10 | GRADING AND GRAVELLING WORKS | 442973.88 | 0 | 442973.88 | 442973.88
| Sub Total | 516573.88 | 0 | 516573.88 | 516573.88
| ADD 16% VAT | 82651.8208 | 0 | 82651.8208 | 82651.8208
| Grand total | 599225.7008 | 0 | 599225.7008 | 599225.7008
| ……………………………………. ……………………… |  | ………………………………………………….. ……………………………
| Contractor's Representative Date |  | County Roads Engineer Date
……………………………………. ……………………………
Road Inspector Date

## BQ No.1
Contract Name: Borborwet Banda- Mereonik Road |  | Contractor : Kossi And Siju Ltd
Contract No. CGK/RD/MT/2016/17- 16 |  | IPC NO.: Final
SUMMARY OF BILL OF ITEMS: General Items |  | DATE: 19/03/2018 |  |  |  |  | Fin. Year 2016-17
|  | UNIT | QUANTITIES |  |  |  |  | AMOUNT
ITEM | DESCRIPTION |  | BOQ | PREVIOUS | THIS | TO-DATE | RATE | KSHS
KSHS
1.01 | Allow a prime cost sum of Kshs.10,000 for Engineer's miscellaneos accont | P.C. sum | 1 |  | 1 | 1 | 10000 | 10000
| Total | [6 empty] | 10000
| ……………………………………. ……………………… |  | ………………………………………………….. ……………………………
| Contractor's Representative Date |  | County Roads Engineer Date
……………………………………. ……………………………
Road Inspector Date

## BQ No. 4
Contract Name: Borborwet Banda- Mereonik Road |  | Contractor : Kossi And Siju Ltd
Contract No. CGK/RD/MT/2016/17- 16 |  | IPC NO.: Final
SUMMARY OF BILL OF ITEMS: Site Clearance |  | DATE: 19/03/2018 |  |  |  |  | Fin. Year 2016-17
|  | UNIT | QUANTITIES |  |  |  |  | AMOUNT
ITEM | DESCRIPTION |  | BOQ | PREVIOUS | THIS | TO-DATE | RATE | KSHS
KSHS
4.01 | Light Bush Clearing | M² | 9300 | 0 | 9300 | 9300 | 4 | 37200
| Total | [6 empty] | 37200
| ……………………………………. ……………………… |  | ………………………………………………….. ……………………………
| Contractor's Representative Date |  | County Roads Engineer Date
……………………………………. ……………………………
Road Inspector Date

## BQ No. 8
Contract Name: Borborwet Banda- Mereonik Road |  | Contractor : Kossi And Siju Ltd
Contract No. CGK/RD/MT/2016/17- 16 |  | IPC NO.: Final
SUMMARY OF BILL OF ITEMS: Drainage Works |  | DATE: 19/03/2018 |  |  |  |  | Fin. Year 2016-17
|  | UNIT | QUANTITIES |  |  |  |  | AMOUNT
ITEM | DESCRIPTION |  | BOQ | PREVIOUS | THIS | TO-DATE | RATE | KSHS
KSHS
8.01 | Excavate in soft material for pipe culverts and subsoil drains, headwalls, wingwalls, apron toe walls and drop inlets, minor drainage structures and compact as specified or directed by the engineer | M³ |  | 0 | 0 |  |  | 0
8.02 | As for Item 8.01 but in Hard Material |  |  |  | 0 |  |  | 0
8.03 | Provide, lay and joint 600mm diameter precast concrete pipes |  |  | 0 | 0 |  |  | 0
8.04 | As for item 8.03 but 900mm dia. Concrete pipes for cross culverts |  |  | 0 | 0 |  |  | 0
8.06 | Provide and place class 15/20 concrete to beds, surrouns and haunches |  |  | 0 | 0 |  |  | 0
8.07 | Provide and place class20/20 concrete to headwalls, wingwalls, aprons toe walls, inlets and outlets to pipe culverts including formwork |  |  | 0 | 0 |  |  | 0
8.08 | Install masonry scour checks at designated points as directed on site by the Engineer | No |  |  | 0 |  |  | 0
8.09 | Desilting of Existing culverts | M | 88 |  | 88 |  | 300 | 26400
| Total | [6 empty] | 26400
| ……………………………………. ……………………… |  | ………………………………………………….. ……………………………
| Contractor's Representative Date |  | County Roads Engineer Date
……………………………………. ……………………………
Road Inspector Date

## BQ No.10
Contract Name: Borborwet Banda- Mereonik Road |  | Contractor : Kossi And Siju Ltd
Contract No. CGK/RD/MT/2016/17- 16 |  | IPC NO.: Final
SUMMARY OF BILL OF ITEMS: Grading and Graveling Works |  | DATE: 19/03/2018 |  |  |  |  | Fin. Year 2016-17
|  | UNIT | QUANTITIES |  |  |  |  | AMOUNT
ITEM | DESCRIPTION |  | BOQ | PREVIOUS | THIS | TO-DATE | RATE | KSHS
KSHS
10.01 | Heavy grading to remove high spots and moving materials to fill potholes , corrugations and wheel ruts and reshape the surface to the specified camber | M² | 8370 | 0 | 8370 | 8370 | 8.5 | 71145
10.03 | Provide,process and compact 120mm thick compacted gravel wearing course across full width of the carriageway as directed by the Engineer |  | 401.76 | 0 | 401.76 | 401.76 | 925.5 | 371828.88
| Total | [6 empty] | 442973.88
| ……………………………………. ……………………… |  | ………………………………………………….. ……………………………
| Contractor's Representative Date |  | County Roads Engineer Date
……………………………………. ……………………………
Road Inspector Date