Republic of Kenya											County Government of Wajir

FINANCE AND ECONOMIC PLANNING DEPARTMENT

ECONOMIC PLANNING & BUDGETING SECTION - ANNUAL WORKPLAN (FY 2016/17)

| OUTPUT DESCRIPTION | ACTIVITIES | TIME FRAME | RESOURCES REQUIRED | BUDGET ESTIMATE IN Kshs |
| --- | --- | --- | --- | --- |
| Preparation of Annual Development Plan | - Collection of Departmental Reports - Compiling the final report | 13th July – 25th August 2015 | - Stationery | 0 |
|  |  |  | - Airtime/Internet | 0 |
|  |  |  | - Daily Subsistence Allowances | 650,000 |
|  |  |  | - Conference facilities | 0 |
| SUB-TOTAL |  |  |  | 650,000 |
| Preparation of C-BROP | - Public Expenditure Review - Getting departmental reports - Compiling the final report | By 19th September 2016 | - Stationery | 10,000 |
|  |  |  | - Airtime/Internet | 0 |
|  |  |  | - Daily Subsistence Allowances (retreat) | 900,000 |
|  |  |  | - Advertising, Awareness and Publicity Campaigns | 100,000 |
|  |  |  | - Refined Fuels and Lubricants | 20,000 |
|  |  |  |  | 1,020,000 |
| Monitoring & Evaluation and reporting | Bi-Annually County Monitoring and Evaluation and field visits | 25th September – 28th October 2016 | - Refined Fuels and Lubricants for Field Visit | 300,000 |
|  |  |  | - Subsistence allowances (field Visits, 20 days | 1,652,000 |
|  |  |  | - Airtime/Internet | 20,000 |
|  |  |  |  | 1,972,000 |
| Tracking the CIDP Implementation (2013-16) and preparation of draft report | - Collect projects from departments - Consolidate for the whole county - Validate with all departments - Retreat on final report | 1st -30th November 2016 | - Conference facilities for chief officers, directors and technical officers | 600,000 |
|  |  |  | - Stationaries | 20,000 |
|  |  |  | Daily Subsistence Allowances for 10 days | 896,000 |
|  |  |  | - Publishing and printing | 400,000 |
|  |  |  |  | 1,916,000 |
| Preparation of County Fiscal Strategy Paper | - Preparation of CFSP | 1-20th December 2016 | - Conference Facilities | 300,000 |
|  |  |  | - Daily Subsistence Allowances | 890,000 |
| SUB-TOTAL |  |  |  | 1,190,000 |
| Updating of the county Profile & collection projects priorities for CIDP 2018-2022 | - Development of statistical tools - Field Data Collection - Data entry - Data analysis and validation - Publishing and dissemination | 10th -31st January 2017 1st March – 20th April 2017 | - Stationaries | 100,000 |
|  |  |  | - Daily Subsistence Allowances (Field Visits) | 2,548,000 |
|  |  |  | - Refined Fuels and Lubricants | 400,000 |
|  |  |  | - Conference facilities | 600,000 |
|  |  |  | - Daily Subsistence Allowances(retreat) | 1,276,000 |
|  |  |  | - Publishing and dissemination | 500,000 |
| SUB-TOTAL |  |  |  | 5,424,000 |
| Budget Estimates | - Collection of departmental proposal - Compiling of the final | 1st February - 15th February 2016 | - Conference facilities – Chief officers, Directors, and technical officers from departments) | 300,000 |
|  |  |  | - Airtime/Internet | 30,000 |
|  |  |  | - Refined Fuels and Lubricants | 200,000 |
|  |  |  | - Daily Subsistence Allowances (Public participation) | 1,940,000 |
|  |  |  | - Advertising, Awareness and Publicity Campaigns (Public participation) | 200,000 |
|  |  |  | - Conference facilities (At wards public participation) | 1,200,000 |
|  |  |  | - Retreat (Compilation of the final budget) | 912,800 |
|  |  |  |  | 1,212,800 |
| Loading of the Budget in the IFMIS system | - Loading the budget | May 2017 | - Daily Subsistence allowance | 1,108,100 |
| SUB-TOTAL |  |  |  | 1,108,100 |
| Project implementation status | - Field monitoring and evaluation | June 1st – 10th 2017 | - Daily subsistence allowance | 672,000 |
|  |  |  | - Refined fuel and lubricants | 100,000 |
| - SUB-TOTAL |  |  |  | 772,000 |
| Mid-year performance contract evaluation | - Evaluation and reports for performance contract | 5th – 10th January | - Stationeries | 20,000 |
| RRI to fast-track performance contract | - Evaluation and reports for performance contract | 15th – 25th June 2017 | - Stationeries | 100,000 |
| SUB-TOTAL |  |  |  | 120,000 |
| GRAND TOTAL |  |  |  | 15,384,900 |
| CGW |  |  |  | 12,384,900 |
| PARTNERS |  |  |  | 3,000,000 |

Prepared By:

Mohamed Yunis Sheikh

Senior Economist II